## Duration
Tasks | planned duration (weeks) | actual duration (weeks) | cumulative planned durations | cumulative actual durations | corrective
buy the land | 1 | 1 | 1 | 1 | 1
hire workers | 1 | 2 | 2 | 3 | 3 | Current Progress | 18
build warehouses | 4 | 3 | 6 | 6 | 6 | Max Planned | 22
setup the irrigation system using automatic irrigation system | 3 | 1 | 9 | 7 | 7 | Days Left | 2
setup an energy supply system using solar tracking system and energy manager , | 3 | 1 | 12 | 8 | 8 | Requires rates | 2
prepare the land (use some fertilizer) | 1 | 2 | 13 | 10 | 10
plant some cowpeas | 1 | 1 | 14 | 11 | 11
manage pest and diseases, | 1 | 1 | 15 | 12 | 12
harvesting | 1 | 3 | 16 | 15 | 15
store the crops using smart dryer | 1 | 3 | 17 | 18 | 18
manage access using Face Recognition | 1 |  | 18 | #N/A | 20
Start selling product | 4 |  | 22 | #N/A | 22

## Cost
Tasks | planned cost F CFA | actual cost F CFA | cumulative planned cost | cumulative actual cost | corrective
buy the land | 5000000 | 6000000 | 5000000 | 6000000 | 6000000
hire workers | 3000000 | 2700000 | 8000000 | 8700000 | 8700000 | Current Progress | 18225000
build warehouses | 4000000 | 2500000 | 12000000 | 11200000 | 11200000 | Max Planned | 21600000
setup the irrigation system using automatic irrigation system | 3800000 | 3000000 | 15800000 | 14200000 | 14200000 | Days Left | 2
setup an energy supply system using solar tracking system and energy manager , | 3000000 | 2500000 | 18800000 | 16700000 | 16700000 | Requires rates | 1687500
prepare the land (use some fertilizer) | 500000 | 375000 | 19300000 | 17075000 | 17075000
plant some cowpeas | 300000 | 225000 | 19600000 | 17300000 | 17300000
manage pest and diseases, | 0 | 0 | 19600000 | 17300000 | 17300000
harvesting | 0 | 0 | 19600000 | 17300000 | 17300000
store the crops using smart dryer | 1000000 | 925000 | 20600000 | 18225000 | 18225000
manage access using Face Recognition | 1000000 |  | 21600000 | #N/A | 19912500
Start selling product | 0 |  | 21600000 | #N/A | 21600000