## Duration
Tasks | planned duration (weeks) | actual duration (weeks) | cumulative planned durations | cumulative actual durations | corrective
start managing visitors with no Reesa and faso music | 5 | 3 | 5 | 3 | 3
implement the image recognition system to detect disease of plants | 4 | 2 | 9 | 5 | 5 | Current Progress | 50
try to sell our product abroad, look for international partners for exportation | 48 | 45 | 57 | 50 | 50 | Max Planned | 61
increase our effectives | 4 |  | 61 | #N/A | 61 | Days Left | 1
[6 empty] | Requires rates | 11

## Cost
Tasks | planned cost | actual cost | cumulative planned cost | cumulative actual cost | corrective
start managing visitors with no Reesa and faso music | 8000000 | 7800000 | 8000000 | 7800000 | 7800000
implement the image recognition system to detect disease of plants | 3000000 | 3500000 | 11000000 | 11300000 | 11300000 | Current Progress | 11300000
try to sell our product abroad, look for international partners for exportation | 1000000 |  | 12000000 | #N/A | 13150000 | Max Planned | 15000000
increase our effectives | 3000000 |  | 15000000 | #N/A | 15000000 | Days Left | 2
[6 empty] | Requires rates | 1850000